## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Aliya Aftab | 2025-11-10 | HADOOP_HOME Exception: PySpark threw FileNotFoundException on write operation due to missing Winutils. | Sprint 1 | Aliya Aftab | Logical | Downloaded winutils.exe & hadoop.dll and configured System Variables. | 2025-11-11 | Closed | Required PC restart to apply.
2 | Aliya Aftab | 2025-11-10 | Timestamp Parsing Crash: Data cleaning failed on mixed date formats (YYYY-MM-DD vs DD/MM/YYYY). | Sprint 1 | Aliya Aftab | Logical | Implemented coalesce with try_to_timestamp to handle multiple formats. | 2025-11-10 | Closed | Fixed in clean_data.py.
3 | Aliya Aftab | 2025-11-13 | Import Error: NameError: name 'desc' is not defined during analysis script execution. | Sprint 2 | Aliya Aftab | Standards | Added missing import: from pyspark.sql.functions import desc. | 2025-11-13 | Closed | Syntax error corrected.
4 | Aliya Aftab | 2025-11-20 | Dashboard Crash: Streamlit app failed with ValueError when all filters were deselected. | Sprint 4 | Aliya Aftab | User Interface | Added conditional check if not df_filtered.empty: before plotting charts. | 2025-11-20 | Closed | Improved error handling.
5 | Aliya Aftab | 2025-11-22 | Date Range Locked: Dashboard date picker restricted to a single day due to limited test data. | Sprint 4 | Aliya Aftab | Logical | Updated generation script to simulate data over a 7-day period. | 2025-11-22 | Closed | Test data range expanded.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others